## Sheet1
Unique ID | User story | Story points | Assignee | Reviewers 1 | Reviewers 2
Frontend | MUN
Acadmic papers
1 | As a MUN admin/user, I should be able to view the academic papers and conference resolutions | 3 | Menna | Habiba | Marwan
2 | As a MUN admin, I should be able to upload academic papers and conference resolutions | 3 | Menna | Habiba | Marwan
3 | As a MUN admin, I should be able to delete academic papers and conference resolutions | 3 | Menna | Habiba | Marwan
Committees
4 | As a MUN admin, I should be able to create commitees/council's pages | 3 | Mariam | Yomna | Dalia
5 | As a MUN admin, I should be able to delete commitees/council's pages | 3 | Mariam | Yomna | Dalia
6 | As a MUN admin, I should be able to update commitees/council's pages | 3 | Mariam | Yomna | Dalia
7 | As a MUN admin/user, I should be able to view committee’s/council’s pages | 3 | Mariam | Yomna | Dalia
Messages
8 | As a user, I should be able to write a message to a committee leaving my email address | 3 | Dalia | Menna | Mariam
Subscription
9 | As a user, I should be able to subscribe to a mailing service | 3 | Yara | Doha | Ziad
Achievements
10 | As a MUN admin, I should be able to create achievement posts | 3 | Yomna | Yara | Ziad
11 | As a MUN admin, I should be able to delete achievement posts | 3 | Yomna | Yara | Ziad
12 | As a user/MUN admin, I should be able to view achievement posts | 3 | Yomna | Yara | Ziad
Photos
13 | As a user, I should be able to view photos in a slideshow on the homepage | 3 | Yara | Menna | Habiba
Mission and vision
14 | As a user/MUN admin, I should be able to read MUN’s mission and vision | 3 | Yomna | Dina | Dalia
GUCMUN description
15 | As a MUN admin/user, I should be able to view MUN’s description | 3 | Yara | Dalia | Ziad
Albums
16 | As a MUN admin, I should be able to create albums | 3 | Dina | Mariam | Doha
19 | As a MUN admin, I should be able to delete albums | 3 | Dina | Mariam | Doha
20 | As a MUN admin, I should be able to update albums (Change name, description and photos) | 3 | Dina | Mariam | Doha
21 | As a user/ MUN admin, I should be able to view albums | 3 | Dina | Mariam | Doha
Events
23 | As a MUN admin, I should be able to create events and specify their details | 3 | Habiba | Yomna | Ziad
24 | As a MUN admin, I should be able to update events | 3 | Marwan | Yomna | Ziad
25 | As a MUN admin, I should be able to delete events | 3 | Habiba | Yomna | Ziad
26 | As a user, I should be able to read titles and summaries about events | 3 | Marwan | Yomna | Ziad
27 | As a user/MUN admin, I should be able to view an event | 3 | Marwan | Yasmin | Menna
28 | As a user, I should be able to view events within the same month | 5 | Marwan | Yasmin | Menna
29 | As a user, I should be able to view future events with 'coming soon' text if no details are provided for the upcoming event. | 3 | Dalia | Yasmin | Menna
Live Feed
30 | As a user/admin, i should be able to view live feed from social media | 13 | Ziad | Doha | Yara
Hierarchy
31 | As a user, i should be able to view hierarchy | 3 | Yasmin | Mariam | Marwan
HUB
32 | As a user/admin, I should be able to login to the website | 5 | Doha | Ziad | Yara
33 | Authentication and authorization of all frontend user stories | 13 | Doha | Ziad | Yara
34 | As a user, I should be able to navigate through club domains | 5 | Yara | Ziad | Doha
Backend
Hierarchy
35 | As an admin, I should be able to insert new board member in the hierarchy | 2 | Yomna | Mariam | Marwan
36 | As a user, I should be able to view all board members within the hierarchy | 2 | Yasmin | Mariam | Marwan
37 | As an admin, I should be able to delete board member in the hierarchy | 2 | Yomna | Mariam | Marwan
| As an admin, I should be able to update information about a board member in the hierarchy | 2 | Yasmin | Mariam | Marwan
Events
38 | As a user, I should be able to get all MUN events | 3 | Habiba | Yasmin | Menna
39 | As a user I should be able to provide feedback on event | 3 | Habiba | Yasmin | Menna