## Sheet1
Uniuqe ID | User story | Epic ? | Priority | Backend | Frontend
1 | AWG
1.1 | As a user, I should be able to view all the participating AWG’s Subdomains. |  | High |  | Yara, Yomna
1.2 | As a user, I should be able to be redirected from the hub to the subdomain of any of the participating clubs. |  | High |  | Yara
1.3 | As a user, I should be able to view the home page. |  | High |  | Mariam
1.4 | As a user ( registered / unregistered / admin ), i can see a brief description about every club to have a quick background for each club |  | High | Ziad | Yomna
1.5 | As an admin of a certain club, i should be able to modify the brief description of this club only |  | hehe | Ziad
1.6 | As a hub admin, I should be able to ( create / delete / edit ) announcements related to the hub. |  | Medium | Yara, Yasmin | Yara, Yasmin, Ziad, Habiba
1.7 | As a user, i should be able to see the announcements that are posted on the hub as to be updated with the news |  | Medium | Yara | Yara
1.8 | As a user I should be able to sign up to have an account on the hub to view restricted content |  | High | Doha, Yasmin | Doha, Ziad
1.9 | As a user, I should be able to login to his/her account on the hub. |  | High | Doha | Doha
1.1 | As an admin, I should be able to view users’ profiles to see all their information. |  | High | Yasmin | Ziad
1.11 | As an admin, I should be able to add/ edit/ delete users. |  | High | Yasmin, Doha | Ziad, Doha
1.12 | As a hub admin, I should be able to edit FAQs section to provide answers and delete the repeated questions |  | Medium | Menna | Menna
1.13 | 1. As a user, I should be able to search for events or announements to find what I’m looking for faster. | epic | low | Ziad, Doha | Doha, Ziad
1.14 | As a hub admin, I should be able to add, edit and delete FAQs to keep them up to date. |  | Medium | Menna | Marwan, Dalia, Yasmin
1.15 | 1. As a user, I should view FAQs to know about the Frequently Asked Questions of the AWGs |  | Medium | Menna | Menna
2 | Mun
2.1 | As a user, I should be able to view MUN’s Mission and Vision to know more about MUN |  | Low | Menna | Yomna
2.2 | As an admin, I should be able to edit MUN’s Mission and Vision to keep it updated |  | hehe | Menna
2.3 | As a user, I should be able to view MUN’s achievements to know more about MUN |  | Medium | Doha | Yomna, Yasmin
2.4 | As an mun admin, I should be able to add, edit and delete the achievements section to keep it updated for the users. |  | Medium | Doha | Yasmin
2.5 | As a user, I should be able to view MUN’s hierarchy. |  | low |  | Yasmin
2.6 | As an admin, I should be able to edit the hierarchy and the additional details to keep the hierarchy updated for the users. |  | low | Yomna
Events:
2.7 | As an admin I should be able to post about the annual events to be able to share them with the users |  | High | Marwan | Marwan
2.8 | As a user i should be able to see the title and the summary of any event to be able to know about it |  | High | Marwan | Marwan
2.12 | As a user I should be able to view photos with the description to be able to know more about GUCMUN |  | Low | Menna
2.13 | As a user i should be able to view description on what GUCMUN does and how they help in academic, personal and community development |  | High | Menna | YOMNA??
2.14 | As an admin I should be able to edit the description of what GUCMUN does |  | Low | Doha
2.15 | As a user i should be able to view galleries of merchandise made every year. |  | High | Dina | Dina
2.16 | As an admin i should be able to edit galleries of merchandise. |  | High | Dina | Dina
2.17 | As a registered/unregistered user i should be able to Leave a message on the website to reach/contact the admins. |  |  | Dalia | Dalia
2.18 | As an admin i should be able to update reply status of the messages |  |  | Dalia | Dalia
2.19 | As an admin I should authorize team members to have control |  |  | Mariam | Ziad
2.2 | As an admin, I should be able to add/ edit/ delete pages for every committee, council and office as well as adding/ editing/ removing descriptions, team members and events to make sure that they are always up to date |  | High | Mariam | Mariam
2.21 | As a user, I should be able to view pages for every committee, council and office to get to know more about each one of them |  | High | Mariam | Mariam
2.22 | 1. As a user, I should be able to register online by adding my basic information and my preferred council/office to get the chance to join mun. |  | low | Yomna | Yomna
2.23 | 1. ly or making the registration available to externals to limit participants of the registration according to mun's preferences. |  | hehe | lol | lol
2.24 | 2. As an admin, I should be able to edit field areas to match it with the corresponding event. |  | hahaha | lol | lol
2.25 | 3. As an admin, I should be able to upload academic papers and conference resolutions to my respective page to allow users to view them |  | medium | Habiba, Menna | Menna
2.26 | 4. As a user, I should be able to view academic papers and conference resolutions to navigate through text. |  | medium | Menna | Menna
2.27 | 5. As a user, I should be able to limit years of academic papers and conference resolutions I want to see, to limit results. |  | low | Yomna | lol
2.28 | 6. As an admin, I should be able to create,edit or delete timeline to adapt to possible changes in timeline. |  | high | marwan | marwan
2.29 | 7. As a user, I should be able to see a small timeline of events happening this month to be updated with events taking place in the meantime. |  | medium | yomna | marwan
2.3 | 8. As a user, I should be able to view details and photos of an event when I hover over it to clearly understand an event. |  | hahaha | lol | lol
2.3.2 | As a user, I should be able to view the main events |  | High | marwan | Marwan
2.3.3 | As a user, I should be able to view future events with ‘coming soon’ text if no details are provided for the upcoming event. |  | low | yomna | Marwan
2.31 | As a user, I should be able to rate the events I view anonymously. |  | High | ziad | Marwan
2.32 | As a user, I should be able to send anonymous feedback on the events I view to express my opinion. |  | High |  | Marwan
2.33 | As a user, I should be able to subscribe to a mailing service to receive information about important events and announcements. |  | medium | Yara | Yara
| An admin should be able to get list of subscribers |  | medium | Yara | Yara
2.34 | As a user I should view live streaming of MUN events | epic | low |  | Yomna
2.35 | As a user I should be able to view live feed | epic | low |  | Ziad

## Sheet2
Uniuqe ID | User story | Epic | Priority | Backend | Frontend
Users:
1 | An admin can create/delete users |  | high | Yasmin, Doha | Doha, Ziad
2 | Mun admin can give control to team members to do changes on the website |  | low | Mariam | Ziad
3 | Users can sign up on the hub |  | high | Doha | Doha
4 | User can logout |  | high |  | Doha
5 | Users can edit their information and add display picture |  | medium | Yasmin | Ziad
6 | Admins can view list of users |  | medium | Yasmin | Ziad
7 | Users can login |  | high | Doha | Doha
8 | Users can delete their accounts |  | low | Yasmin, Doha | Doha
Announcements:
9 | Admins can create/edit/delete announcements displayed on the hub to give more information to users |  | medium | Yara | Ziad, Yasmin, Habiba
10 | As a user, i should be able to view the announcements that are posted on the hub as to be updated with the news |  | medium | Yara | Yara
FAQs
11 | Admins can create/edit/delete FAQs displayed on the hub to keep them updated |  | medium | Menna | Yasmin, Marwan, Dalia
12 | Users can view FAQs |  | medium | Menna | Menna
Events
13 | An MUN admin should be able to create events and specify their details |  | High | Marwan | Marwan
14 | An MUN admin should be able to update or delete events |  | medium | Marwan | Marwan
15 | A user should be able to read titles and summaries about events |  | medium | Marwan | Marwan
16 | A user should be able to read titles and summaries about events |  | High | Yomna | Marwan
17 | As a user, I should be able to view events within the same month |  | medium | Yomna | Marwan
18 | As a user, I should be able to view future events with 'coming soon' text if no details are provided for the upcoming event. |  | low | Yomna | Marwan
19 | As a user I should be able to rate events and see rating of events |  | medium | Ziad | Marwan
20 | As a user, I should be able to send anonymous feedback on the events I view to express my opinion and view feedbacks |  | medium | Dina | Marwan
21 | As a user, I should be able to see a small timeline of events happening this month to be updated with events taking place in the meantime. |  | low | Yomna | Marwan
Subscribers
22 | 3. As a user, I should be able to subscribe to a mailing service to receive information about important events and announcements. |  | low | Yara | Yara
23 | As an admin, I should be able to get the list of the subscribed emails |  | low | Yara | Yara
Libraries
24 | As an admin, I should be able to upload academic papers and conference resolutions to my respective page to allow users to view them |  | High | Habiba, Menna | Menna
25 | As a user, I should be able to view academic papers and conference resolutions to navigate through text. |  | High | Habiba, Menna | Menna
26 | As a user, I should be able to limit years of academic papers and conference resolutions I want to see, to limit results. |  | low | Yomna
Messages
27 | As a registered/unregistered user i should be able to Leave a message on the website to reach/contact the admins. |  | medium | Dalia | Dalia
28 | An admin should be able to view/delete the list of messages directed to his/her committee |  | low | Dalia | Dalia
29 | An admin can update the status of messages (replied or not) and delete messages |  | medium | Dalia | Dalia
Mission & Vision
30 | As a user, I should be able to view MUN’s Mission and Vision to know more about MUN |  | medium | Yomna, Menna | Yomna
31 | As an admin, I should be able to edit MUN’s Mission and Vision to keep it updated |  | medium | Menna
Hierarchy
32 | As a user, I should be able to view MUN’s hierarchy. |  | low |  | Yasmin
Recruitment Forms
33 | As a user, I should be able to register online by adding my basic information and my preferred council/office to get the chance to join mun. (Recruitment forms) |  | medium | Dina | Yomna
34 | As an MUN Admin, I should be able to retrieve all recruitment forms responses |  | low | Yomna | Yomna
Achievements
35 | As a user, I should be able to view MUN’s achievements to know more about MUN |  | medium | Doha | Yomna
36 | As an mun admin, I should be able to add, edit and delete the achievements section to keep it updated for the users. |  | medium | Doha | Yomna, Yasmin
Homepage
37 | Users should be able to view the homepage for AWG |  | high |  | Mariam
Authentication & Authorization
| Access Levels of each user type is determined and implemented. |  | high | Doha | Doha
Extra Features
| As a user I should be able to view live feed from social media | EPIC | low |  | ziad
| As a user I should view live streaming of MUN events | EPIC | low |  | yomna
| As a user I should be able to search for events using names and tags on the hub and get information from subdomains As a user I should be able to search for AWGs on the hub to get more information As a user I should be able to search using tags on the hub to get information from subdomains related to announcements, achievements, faqs and albums | EPIC | medium | Ziad, Doha | Doha