## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
| As a user I should be able to search for events using names and tags on the hub and get information from subdomains | 8 | Doha | Yara | Ziad
| As a user I should be able to search for AWGs on the hub to get more information | 5 | Ziad | Yara | Doha
| As a user I should be able to search using tags on the hub to get information from subdomains related to announcements, achievements, faqs and albums | 8 | Ziad | Yara | Doha
| As an MUN admin, I should be able to assign my respective page to a team member to have control over the page | 5 | Mariam | Dalia | Menna
Forms Template on MUN
| As an MUN admin, I should be able to create a form template using MongoDB | 5 | Yomna | Yasmin | Dina
| As a user, I should be able to view the form template using MongoDB and test it | 3 | Dalia | Doha | Habiba
| As an MUN admin, I should be able to update the form template using MongoDB | 5 | Yomna | Ziad | Dina
| As an MUN admin, I should be able to delete the form template using MongoDB and test it | 3 | Menna | Dalia | Mariam
Recruitment Forms on MUN
| As an MUN admin, I should be able to see all Recruitment form responses using MongoDB and test it | 3 | Yomna | Dina | Yara
| A user should be able to fill in the registration form | 5 | Dina | Habiba | Ziad
Users
| Testing: As a hub admin, I should be able to create or delete users | 2 | Yasmin |  | Doha
| Testing: As a hub admin, I should be able to read or update users' information | 2 | Yasmin |  | Doha
| Testing: As a user, I should be able to read or update my information | 2 | Yasmin |  | Doha
Announcements
| Testing: As a hub admin, I should be able to create or delete announcements on the hub | 2 | Yara | Ziad | Doha
| Testing: As a hub admin, I should be able to read or update announcements on the hub | 2 | Yara | Ziad | Doha
FAQs
| Testing As a hub admin, I should be able to create, update or delete questions and answers in FAQs on the hub | 2 | Menna | Mariam | Dalia
| Testing: As a user/admin, I should be able to read questions and answers in FAQs on the hub | 2 | Menna | Mariam | Dalia
Clubs on the hub
| Testing: As a user/admin, I should be able to read description of the club | 2 | Ziad | Yara | Doha
| Testing: As an admin, I should be able to update brief description of the club | 2 | zyad | Yara | Doha
Committees
| Testing: An MUN admin should be able to create or delete commitees/council's pages | 2 | Mariam | Menna | Dalia
| Testing: An MUN admin should be able to update commitees/council's pages | 2 | Mariam | Menna | Dalia
| Testing: An MUN admin/user should be able to read committee’s/council’s pages | 2 | Mariam | Menna | Dalia
Photos
| Testing: An MUN admin should be able to create or delete photos | 2 | Habiba | Dina | Marwan
| Testing: An MUN admin should be able to update descriptions about photos | 2 | Habiba | Dina | Marwan
| Testing: A user/admin should be able to view photos | 2 | Habiba | Dina | Marwan
Events
| Testing: An MUN admin should be able to create events and specify their details | 2 | Marwan | Habiba | Yasmin
| Testing: An MUN admin should be able to update or delete events | 2 | Marwan | Habiba | Yasmin
| Testing: A user should be able to read titles and summaries about events | 2 | Marwan | Habiba | Yasmin
| Testing: A user/admin should be able to view an event | 2 | Yasmin | Doha
| Testing: As a user, I should be able to view events within the same month | 2 | Yasmin | Doha
| Testing: As a user, I should be able to view future events with 'coming soon' text if no details are provided for the upcoming event. | 2 | Yara | Doha | Ziad
Rating
| Testing: As a user, I should be able to rate events | 2 | Zyad | Yomna | Habiba
| Testing: As a user/admin, I should be able to view ratings about events | 2 | Zyad | Yomna | Habiba
Feedback
| Testing: As a user, I should be send anonoymous feedback events | 2 | Dina | Menna | Yasmin
| Testing: As a user/admin, I should be able to read feedbacks on events | 2 | Dina | Menna | Yasmin
Subscription
| Testing: As a user, I should be able to subscribe to a mailing service | 2 | Yara | Doha | Ziad
| Testing: As an admin, I should be able to get the list of the subscribed emails | 2 | Yara | Doha | Ziad
Mission and vision
| Testing: A user/admin should be able to read MUN’s mission and vision | 2 | Menna | Ziad | Marwan
| Testing:An MUN admin should be able to update MUN’s mission and vision | 2 | Yasmin
GUCMUN description
| Testing: An admin/user should be able to view MUN’s description | 2 | Menna | Ziad | Yara
| Testing: An MUN admin should be able to update MUN’s descriptions | 2 | Yasmin
Messages
| Testing: A user should be able to write a message to a committee leaving my email address | 2 | Dalia | Doha | Mariam
| Testing: An admin should be able to view the list of messages directed to his/her committee | 2 | Dalia | Doha | Mariam
| Testing: An admin should be able to delete messages from the list of messages | 2 | Dalia | Doha | Mariam
Acadmic papers
| Testing: An admin should be able to upload or delete academic papers and conference resolutions | 2 | Habiba | Menna | Yasmin
| Testing: An admin/user should be able to view the academic papers and conference resolutions | 2 | Habiba | Menna | Yasmin
Achievements
| Testing:An admin should be able to create or delete achievement posts | 2 | Doha | Yomna | Ziad
| Testing: An admin should be able to update achievement posts | 2 | Doha | Yomna | Ziad
| Testing: A user/admin should be able to read achievement posts | 2 | Dalia | Yomna | Ziad
Albums
| Testing: An admin should be able to create or delete albums | 2 | Dina | Doha | Yomna
| Testing: An admin should be able to update albums (Change name, description and photos) | 2 | Dina | Doha | Yomna
| Testing: A user/admin should be able to view albums | 2 | Dina | Doha | Yomna