## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
AWGs
1 | A user should be able to view FAQs | 3 | Menna | Dalia | Marwan
2 | A hub admin should be able to update FAQs | 3 | Dalia | Yasmin | Menna
3 | A hub admin should be able to create FAQs | 3 | Yasmin | Marwan | Dalia
4 | A user should be able to delete FAQs | 3 | Marwan | Menna | Yasmin
5 | A user should be able to view announcements | 3 | Yara | Ziad | Doha
6 | A hub admin should be able to create announcements | 3 | Ziad | Yara | Doha
7 | A user should be able search subdomains | 3 | Doha | Ziad | Yara
8 | A user should be able to view the homepage for the AWG hub (Header, footer, components) | 3 | Mariam | Yomna | Habiba
9 | A user should be redirected from the hub to the subdomain of any of the clubs | 3 | Habiba | Dina | Yara
10 | A user should be able to view photo of the clubs in a slide show | 3 | Dina | Yomna | Habiba
11 | A user should be able to view description of the clubs in a slide show | 3 | Yomma | Dina | Doha
| Total | 33